## Bugs Status
Priority/Severity | Defect Nu | Tkt No. | Screen Names | Description | Steps | Expected Result | Actual Result | OS Version | Dev Comments/Version | Test Status (Pass/Fail) | Test Comments | V1.3.07 Universal APK
High | 1 |  | Dashboard Widget | Date on Widget are incomplete | 1. Onboard VDP 2. Click on Widget for enter VDP details Page 3. Back to Dashboard Widget | Date on Widget Screenshot should come complete and no cropping allowed |  | Android | - We are taking the snapshot of the screen render on the camera, and we have not any control to show date at particular position. And in the dashboard widget we have to show the round corner, therefore date is cropped. - As per Neeraj, we can park this issue for now, we will check later if any solution is there for that. https://panasonic-iic.atlassian.net/browse/SIFI-3699 | Fail | Solution Awaited | Open
High | 2 |  | VDP Details Page | Audio toggle button disabled after on-board device as well as if user enable and visit any other page like setting or widget then again toggle button disabled | 1. Onboard VDP 2. Click on Widget for enter VDP details Page 3. Enable Audio Toggle Button 4. Visit Setting Page and Back to VDP details Page | Once Enable Audio Toggle Button . It must be need in Enable State untill user not change settings | Audio toggle button getting disabled even after enable by User | Android | Not Supported. Currently we persisting below settings. - detection sensitivity - Image Flip - Active - scenemode - Cloud video - LED Indicator - SD/HD settings | Pass |  | Closed
High | 3 |  | Recording Videos | Recorded video after capturing and saved in photo . After visit photos in phone . This file not shows | 1. Onboard VDP 2. Click on Widget for enter VDP details page 3. Click on Record Button on VDP details Page 4. Stop recording after some time | User must see saved recording in photos | User unable to see saved recording in photos | Android | Fixed | Pass |  | Closed
High | 4 |  | Online/Offline Status | After Power Off device .. App keep showing device in Online status on Widget as well as VDP Details page | 1. Onboard VDP 2.Observe Online status on Widget aswell as VDP Details page 3. Power Off VDP Device | After Power off device must goes Offline and same status should update on Widget as well as VDP details page | Device never show offline status | Android | -As per Metec team, their app is not giving realm time status, it is updating the status after 12 mins. -Please check whether correct status is showing after 12 mins or not. https://panasonic-iic.atlassian.net/browse/SIFI-3702 | Pass | Device shows Offline after 12 min on Dashboard Widget but Details Page still it shows Online | Closed
High | 5 |  | WiFi Password Limit | During On-board VDP user must able to enter WiFi Password upto 20 characters | 1. Click on Add Device 2. Click on Yes button on VDP Instruction Page 3. Enter Password limit | User must able to enter Wifi Password upto 30 Character as per current requirement | User able to enter Wifi password upto 20 Character | Android | - Only 20 characters limit will be there in password. If anywhere it is showing 30 characters, then it should be changed to 20 characters only. https://panasonic-iic.atlassian.net/browse/SIFI-3703 | Pass |  | Closed
High | 6 |  | Weak Wifi Signal Error | Getting Error "Weak Wifi Signal" even after user near to Router | 1. Onboard VDP 2. Keep VDP Device near to Router | Error should come only after signals are weak or user keep vdp far away from Router | User are getting error sometimes for "Weak Wifi Signal" | Android | - Currently in the code, 5 levels are coming for wifi signal strength. We are treating 1st and 2nd level as weak signal. - Queried Metec team why if the device is near router then also we are getting 1st or 2nd level. Once we will get any update, we will inform the QA team. https://panasonic-iic.atlassian.net/browse/SIFI-3704 | Pass | We are getting weak wifi signal error message when device everytime connecting to WiFi Network | Closed
High | 7 |  | Live Feed | Live Feed getting Enable automatically if user disable | 1. Onboard VDP 2. VDP Details Page 3. Disable Live Feed using Live Feed Toggle Button 4. Press Phone Back Button or Back button on VDP Details 5. Live Feed getting enabled | Live Feed must be disabled untill user not enable it using Toggle Button | Live Feed getting enabled even after it disabled by User | Android | Not Supported. Currently we persisting below settings. - detection sensitivity - Image Flip - Active - scenemode - Cloud video - LED Indicator - SD/HD settings | Pass | Solution Awaited | Closed
High | 8 |  | On-boarding | On-boarding failed if user Phone connected with different network and VDP to different Network | 1. Connect Mobile Device with XYZ Network 2. Click on Add Device in MirAIe Application 3. Click on Yes Button 4. Select ZYX network and input password for that network 5. Click on Connect | User must able to On-board without depend on Network use in Mobile Device | On-boarding failed for different network use by Mobile Device and VDP on-board | Android | Not supported. Device and Mobile should be on same n/w while onboarding. | Fail | Solution Awaited | Open
Medium | 9 |  | Brightness and Volume Level | Unable to control Brightness and Volume level for Zoom In recorded or Live Feed | 1. Onboard VDP 2. VDP Details Page 3. Enable Live Feed 4. Zoom In Live Feed | User should able to Control Volume and Brightness for Live Feed and Recorded Video | Unable to control Brightness and Volume level for Zoom In recorded or Live Feed | Android | -This brightness and volume is only for Live Feed, it will not affect recorded videos. - Please check whether it is affected in Live Feed or not. https://panasonic-iic.atlassian.net/browse/SIFI-3705 | Pass |  | Closed
High | 10 | SIFI-3786 | App Crash | After stop recording video , App getting crash | 1. Onboard VDP 2. VDP Details Page 3. Enable Live Feed 4. Record Video 5. Stop Video | Recording should stop and recording saved in album | App crash observed Model : Panasonic Eluga Ray 610 OS : Andriod 9 | Android | Fixed | Pass |  | Closed
High | 11 | SIFI-3846 | VDP Details Page | Unable to record video untill Wi Fi icon not available on VDP Details Page | 1. Onboard VDP 2. VDP Details Page 3. Enable Live Feed 4. Record Video | Recording should not depend on WiFi icon availability | Recording start but it not show recording timer on recording screen | Android | Fixed. | Pass |  | Closed
High | 12 | SIFI-3833 | VDP Details Page | Hide Access Denied dialog since not able to differentiate b/w device offline and Manual reset | 1. Onboard VDP 2. VDP Details Page 3. Enable Live Feed 4. Record Video | Access denied must not visible for device offline | Access denied dialog shows for device offline case | Android | Fixed. | Pass |  | Closed
High | 13 | SIFI-3834 | History Page | Download video shows progress more than 100% | 1. Onboard VDP 2. VDP Details Page 3. History Tab 4. Download Recorded Video | Download video must show progress 100% | Video download showing more than 100% . Refer attached image for your reference | Android | Fixed. | Pass |  | Closed
Medium | 14 | SIFI-3847 | History Page | Recording video timer and date selection pen on History page are overlapping | 1. Onboard VDP 2. VDP Details Page 3. Start Recording 4. Move to History Page | Recording timer and date selection pen should adjust properly on history page | See attachment for Actual Result | Android | Fixed. | Pass |  | Closed
High | 15 | SIFI-3848 | VDP Details Page | SD Video quality option are not showing for user selection | 1. Onboard VDP 2. VDP Details Page 3. SD Video Quality | User must need option select SD video quality option | SD Video Quality option are missing in current implementation | Android | As discussed with Neeraj, that is ok right now, we can take this task in future. | Pass | Accepted | Closed
High | 16 | SIFI-3849 | VDP Details Page | On Scene Mode widget incomplete scene names are showing | 1. Onboard VDP 2. VDP Details Page 3. Scene Mode 4. Change mode from Normal to other | Widget must show complete name for particular scene mode | See attachment for Actual Result | Android | Not able to reproduce. Can you share the screen size and font size, etc when issue is reproducible. Since, I have checked by increasing font size to "Largest" but still not able to reproduce the issue. | Pass |  | Closed
High | 17 | SIFI-3854 | Recording Videos | Capture video recording more than 7 minutes but it saves video for 3 minutes [2 Videos are created] | 1. Onboard VDP 2. VDP Details Page 3. Start Recording 4. Save Recording 5. Move to History Page | History list must show time for original captured video like if video captured for 7 minute it should show accordingly in History list | History list showing 2 videos each 3 minutes | Android | Not able to test, since I have Android 11 device, there videos are saving in internal and I am not able to extract internal videos. Once Metec team resolve that Android 11 issue, then only only I am able to check that issue. | New issue |  | Closed
Medium | 18 | SIFI-3850 | Wi Fi Indicator ON VDP Details Page | Sometimes WiFi indicator on VDP details page invisible | 1. Onboard VDP 2. VDP Details Page | Wi Fi icon must need to shows on VDP Details page except for disconnection case | WiFi icon disppear anytime | Android | Fixed | Pass |  | Closed
High | 19 | SIFI-3845 | Setting Page -Diagnose Device Button | User need to Tap many times on Diagnose Device Button for show Diagnose Page | 1. Onboard VDP 2. VDP Details Page 3. Setting Page 4. Tap on Diagnose Button | One Tap on Diagnose Device Button should take user Diagnose Page | Diagnose Button not responding . It must be press many times or particular corner of button | Android | Fixed | Pass |  | Closed
High | 20 | SIFI-3844 | Setting Page - Change WiFI password | User need to Tap many times on Change Wifi Password for show Change Wifi Password Page | 1. Onboard VDP 2. VDP Details Page 3. Setting Page 4. Tap on Change Wifi Password | One Tap on Change WiFi Password Button should take user Change Wifi Password Page | Change Wifi Password not responding . It must be press many times or particular corner of button | Android | Fixed | Pass |  | Closed
High | 21 | SIFI-3798 | Scan QR Page | Scan QR Page instuction are showing incomplete | 1. Add VDP 2. Select Device Press "Yes" 3. Enter WiFi Credentials 4. Click on Connect 5. Scan QR Page | Instuction below QR Code must need to visible complete . Please make page up and down scrollable for small size phones | Instructions are cropping on Scan QR Code Page | Android | Fixed | Pass |  | Closed
High | 22 | SIFI-3832 | Dashboard | After login MirAIe Application . User able to see Text "Video Door Phone" without added VDP | 1. Login with MirAIe Credentials 2. Observe Dashboard | User must see blank Dashboard in case user login application | "Video Door Phone" text are appearing on Dashboard after login with application. | Android | Fixed | Pass |  | Closed
High | 23 | SIFI-3851 | Room | Added VDP Device not showing in any Particular Room | 1. Add Device in Living Room from Dashboard 2. Open Living Room | User must see VDP device in Living Room | VDP Device not added or showing in Living Room | Android | Fixed | Pass |  | Closed
High | 24 | SIFI-3852 | LED Indicator | LED Indicator toggle button continuesly On/Off | 1. Onboard VDP 2. VDP Details Page 3. Setting Page 4. LED Indicator | User must able to Enable and Disable LED Indicator | Unable to Enable or Disable LED Indicator | Android | Fixed | Pass |  | Closed
High | 25 | SIFI-3853 | Capture Button | Android 9 - Capture button not capturing photo Android 11 - Capture button working but no message for photo saved | 1. Onboard VDP 2. VDP Details Page 3. Click on Capture Button | User must able to capture photo and message should come for "Photo saved to album" | Android 9 : Capture Button not responding Android 11 - No Message for "Phone Saved to album" | Android | Fixed. Validated only on Android 11 device since I don't have any Android 9 device, so checked on Android 9 emulator. | Pass |  | Closed
High | 26 | SIFI-3951 | Room | User not able to on-board VDP Device from Room add Device [Click on Plus Button] | 1. Login with MirAIe Credentials 2. Create New Room or Enter Existing Room 3. Click on Plus Button | User must able to see Video Door Phone in Device List | User not able to see Video Door Phone in Device list from Room | Android | Fixed | Pass |  | Closed
Medium | 27 |  | Push Notification for "Bell Rang" | User not receive push notification if App running in Backgroud/Foreground | 1. Onboard VDP 2. Press "Bell Button" from VDP | User must has to receive push notification in Background/Foreground | User not received push notification | Android | In Progress, debugging with Server team is pending, we will resume work once we got the access. | Pass |  | Closed
Medium | 28 |  | VDP Details Page | Sometimes WiFi indicator on VDP details page invisible and overlap | See attachment for reference. There is no specific steps to reproduce issue |  |  | Android | Fixed | Pass |  | Closed
High | 29 | SIFI-3950 | Toast Message | Capture Snapshot and Recording Video Successfully Toast message not similar to Zeplin Screens | 1. Onboard VDP 2. Click on Widget for enter VDP details page 3. Click on Record and Capture Button on VDP details Page | It must need to show Toast like below 1. Capture Screenshot "Screenshot saved successfully " 2. Recorded Video ""Recorded Video Saved Successfully" |  | Android | Fixed | Pass |  | Closed
High | 30 | SIFI-3953 | Play Recorded Video in Live Feed Off | Live Feed Toggle button in disable state but user can see Capture , Talk and Record option are in enable state if user back from History tab | 1. Onboard VDP 2. Click on Widget for enter VDP details page 3. Disable Live Feed 4 .Click on History Tab 5. Play any recorded Video 6. Come back to VDP details Page | User must see Live Feed to be disable state and other options like capture to be in disable state untill user not enable Live Feed | Live Feed option in disable state but other options like Capture . Talk and Record are enable if User back during Play Recorded Video to VDP details Page | Android | Fixed | Pass |  | Closed
Low | 31 | SIFI-3958 | VDP Details Page | Default Settings Set after Kill Application and Relaunch for Detection Sensitivity , Image Flip , Active Time and Scene Mode | 1. Onboard VDP 2. Click on Widget for enter VDP details page 3. Change setting of Detection Sensitivity , Image Flip , Active Time and Scene Mode to some other than Default 4. Kill Application and Relaunch | User must see settings set for DS , IF , AT and SM before Kill Application | User able to see default Settings DS - off , IF - Normal , AT - 15s and SM - Normal | Android | Fixed, We are getting the values from device and showing it. We observed after offline/online, the values will automatically reset. | Pass |  | Closed
High | 32 | SIFI-3960 | Offline Status | If Device in Offline state still Button for Capture , Talk and Record in enable state | 1. Onboard VDP 2. Click on Widget for enter VDP details page 3. Switch off the device and wait for offline state | For Offline state , Options like Capture , Talk and Record should not show be disable state | Talk , Capture and Record button are in enable state | Android | Fixed | Pass |  | Closed
Medium | 33 | SIFI-3959 | Landscape Video Recording | Recording video timer showing the center of screen | 1. Onboard VDP 2. Click on Widget for enter VDP details page 3. Make screen in Landscape Mode 4. Start Recording | Video Timer should show at the top near to date and current time | Timer showing at the center of screen | Android | Fixed | Pass |  | Closed
High | 34 | SIFI-3948 | Crash | Sometimes Play recorded video crash application . Looks like mediacodec problem | See attached logs for reference |  |  | Android | Fixed | Pass |  | Closed
Medium | 35 | SIFI-3949 | Sri Lanka User | Video Door Phone text are showing in Rooms | 1. Login with Sri lanka User 2. Enter Room | Video Door Phone Text must not visible in Room as well as Dashboard for Sri Lanka User | Video Door Phone Text are visible in Room for Sri Lanka User | Android | Fixed | New issue |  | Closed
High | 36 | SIFI-3962 | Mobile Back Button [Android 9] | Press Mobile Back Button in VDP Details Page App getting Crash | 1. Login with India User 2. On-board VDP 3. VDP Details Page 4. Press Mobile Back Button | User must land to Dashboard smoothly after press Mobile Back Button | App getting Crashed after press mobile back button | Android | Not able to reproduce, but as per logs that is ANR. Fixed as per code. | Pass |  | Closed
Medium | 37 | SIFI-3961 | Detail Page | On low resolution phone showing wifi, HD and battery icon | Orientation change in Detail page | wifi, HD and battery icon should not be visible | wifi, HD and battery icon is visible | Android | Fixed | Pass |  | Closed
High | 38 |  | Dynamic Module APKs | Live feed full screen is not working getting white screen and need to kill the app to use VDP again. (App crashes) |  |  |  | Android | Fixed | Pass |  | Closed
High | 39 |  | Dynamic Module APKs | Live Video Record option is not working getting white screen and need to kill the app to use VDP again. (App crashes) |  |  |  | Android | Fixed | Pass |  | Closed
High | 40 |  | Dynamic Module APKs | Full screen option are showing without play any videos from history tab and if user tap on full screen option getting white screen and need to kill the app to use VDP again. (App crashes) |  |  |  | Android | Fixed | Pass |  | Closed
High | 41 |  | Dynamic Module APKs | SD card videos are not working when tap on full screen option getting white screen and need to kill the app to use VDP again. (App crashes) |  |  |  | Android | Fixed | Pass |  | Closed
Medium | 42 |  | Dynamic Module APKs | Audio toggle button is enabling when user tap on unmute button. |  |  |  | Android | Not an issue, since behaviour is same in Ubell app | Pass |  | Closed
Medium | 43 |  | Dynamic Module APKs | When active time change to always user not getting pop up message showing that (The PIR alarm will stop working in the dormant state, and the battery will run out in the next few hours) |  |  |  | Android | Fixed | Pass |  | Closed
Low | 44 |  | Dynamic Module APKs | Cloud videos are not playing from history tab until unless video downloaded (No response). |  |  |  | Android | In Android, cloud videos can't be directly played, it has to be downloaded first before playing. | Pass |  | Closed
High | 45 |  | Dynamic Module APKs | Present used data details are not showing for T card (SD card) |  |  |  | Android | Fixed | Pass |  | Closed
High | 46 |  | Dynamic Module APKs | App crash after launch VDP devices |  |  |  | Android | Fixed | Pass |  | Closed
High | 47 |  | Dynamic Module APKs | App crash after click on Setting icon |  |  |  | Android | Fixed | Pass |  | Closed
High | 48 |  | Dynamic Module APKs | For Cloud Video Download , User unable to download after press on Cloud Thumbnail. |  |  |  | Android | Fixed | Pass |  | Closed
Medium | 49 |  | Dynamic Module APKs | Audio checkbox should be enabled, when opening vdp detail screen |  |  |  | Android | Fixed | Pass |  | Closed
High | 50 |  | Dynamic Module APKs | Less cloud videos are showing in history tab for selected date |  |  |  | Android | Fixed | Pass | Pass with New Firmware Main firmware 501.0.8.32 / Wi-Fi Version 63.0.1.44 | Closed
Medium | 51 |  | Dynamic Module APKs | in Dark Mode Font Colour change to Blue for some thumbnails and text - Android 11 |  |  |  | Android | Fixed | Pass |  | Closed
High | 52 |  | Dynamic Module APKs | App Crash after click on "Yes" Button in VDP On-boarding Journey and Button Colour for Yes and No are not matching with UX design - Android 8.1.0 [Vivo] | Log will attached in Email |  |  | Android | Fixed | Pass |  | Closed
High | 53 |  | Dynamic Module APKs | Font Icons are in Boxes for Entire VDP - Android 8.1.0 /Android 6 |  |  |  | Android |  | Pass |  | Closed
High | 54 |  | Dynamic Module APKs | HD Option not persistant and not visible |  |  |  | Android | Fixed | Pass |  | Closed
High | 55 |  | Dynamic Module APKs | App Crash after click on Notification and User should land Dashboard - Android 9 | Log will attached in Email |  |  | Android | Reported to Maxwell waiting for his response. | New issue |  | Closed
High | 56 |  | Dynamic Module APKs | Video Door Phone visible in Add Device [Dashboard] and in Room Management for Sri Lanka , Singapore and Thailand User |  |  |  | Android | Fixed | Pass |  | Closed
High | 57 |  | Dynamic Module APKs | Change WiFi Password and Diagnoise Success user staying in Setting Page and after press back button then On-board Dialog coming on VDP Details page | Change Wifi Password > Change Password |  |  | Android | Fixed | Pass |  | Closed
Low | 58 |  | Dynamic Module APKs | "Back light Compensation" and "High light Compesation" Text not accommodate in Circular Widget |  |  |  | Android | Fixed | Pass |  | Closed
High | 59 |  | Dynamic Module APKs | App Crash during Diagnise Journey [Re-onboading] | Log will attached in Email |  |  | Android | Fixed | Pass |  | Closed
High | 60 |  | Dynamic Module APKs | App Crash During On-boarding - Android 11 | Log will attached in Email |  |  | Android | Please keep a watch on this issue, if it is reproduce again, we will work on it. SInce as per the attached logs not able to find the root cause. | New issue |  | Closed
High | 61 |  | Dynamic Module APKs | App crash after click on Unlock Door option and Reset door lock password option - Android 6 , Android 8 and Android 9 | Log will attached in Email |  |  | Android | Fixed | Pass |  | Closed
High | 62 |  | Dynamic Module APKs | App running in Background > Push Notification Received> Tap on Push Notification > User land to VDP Details Page> [Device showing in Offline State and Live Feed toggle button in Disabled State] |  |  |  | Android |  | Pass |  | Closed
High | 63 |  | Dynamic Module APKs | Active Timer for old Firmware Version . User not able to change time from 15 sec to 30 Sec and So |  |  |  | Android |  | Pass |  | Closed
Medium | 64 |  | Dynamic Module APKs | Remove Common Names in Device Rename. Current Names showing are inappropriate like Living Room Light etc. |  |  |  | Android |  | Pass |  | Closed
Medium | 65 |  | Dynamic Module APKs | App Tool Bar for VDP details Page is not correct |  |  |  | Android |  | Pass |  | Closed
High | 66 |  | Dynamic Module APKs | Localization error mentioned in the sheet : Please find the comments in the attached sheet. |  |  |  | Android |  | Pass |  | Closed
High | 67 |  | Dynamic Module APKs | Push Notifications are not localized |  |  |  | Android |  | Pass |  | Closed
High | 68 |  | Dynamic Module APKs | After on-board device not come online . Other option like Image Flip , Active Time etc. showing in Enable State |  |  |  | Android |  | Pass |  | Closed
Medium | 69 |  | Dynamic Module APKs | Live Feed in Disable State by default . User must has to enable every time if User click on widget and in VDP Details Page |  |  |  | Android |  | Pass |  | Closed
High | 70 |  | Dynamic Module APKs | Active Timer not change from 15S to 30S and so on |  |  |  | Android |  | Pass |  | Closed
Medium | 71 |  | Dynamic Module APKs | Text Overlapping for Off board Case |  |  |  | Android |  | Pass |  | Closed
High | 72 |  | Dynamic Module APKs | After on-board >Widget>Details Page>HD icon not showing [user only able see HD option >after press back button and again widget] |  |  |  | Android |  | Pass |  | Closed
High | 73 |  | Dynamic Module APKs | Crashes when clicking on overlay tutorial “Got it” button on vdp details page. |  |  |  | Android | 1.2.144 | Pass |  | Closed
High | 74 |  | Dynamic Module APKs | Overlay icon getting disappear [ Steps : Click on History Tab > Download Cloud Video>Play Cloud Video > After video playback complete>Click on Live Tab ] – Attached image for your reference |  |  |  | Android | 1.2.145 | Pass |  | Closed
High | 75 |  | Dynamic Module APKs | Cloud Video not deleting after seven days- Cloud Team need to fixed |  |  |  | Android | 1.2.145 | New issue |  | Closed
Medium | 76 |  | Dynamic Module APKs | Overlay icon not showing at correct place in Landscape Mode – Attached image for your reference [Observed in one phone] |  |  |  | Android | 1.2.145 | Pass |  | Closed
Low | 77 |  | Dynamic Module APKs | Video Playback from app in landscape mode shows Total Time and Play Time doubled [Steps : Click on History Tab > Download Cloud Video>Play Cloud Video > Click on Full Screen or Landscape mode option ]– Attached image for your reference |  |  |  | Android | 1.2.145 | Pass |  | Closed
High | 78 |  | Dynamic Module APKs | Door Unlock successful message and error message not displayed [Steps : Click on Unlock icon > Enter password> Click on Unlock Button] – Attached image for your reference |  |  |  | Android | 1.2.145 | Pass |  | Closed
Medium | 79 |  | Dynamic Module APKs | Screenshot capture at Dashboard Widget sometimes show “Preview not available” – Attached image for your reference |  |  |  | Android | 1.2.145 - Fixed | Fail |  | Closed
Medium | 80 |  | Dynamic Module APKs | Setting page getting disabled and unable to access Record button , Capture Button ,Mute/Unmute button – Video shared on WhatsApp with Prateek |  |  |  | Android | 1.2.145 - Fixed | Partial Fixed . | Device going offline and never come to Online State Automatic . User has to go Dashboard >Click on Widget | Closed
High | 81 |  | Dynamic Module APKs | Crashes observed during On-boarding | Log will attached in Email |  |  | Android | 1.2.145 - Fixed | New issue |  | Closed
High | 82 |  | Dynamic Module APKs | Crashes observed click on widget – Attached log for reference | Log will attached in Email |  |  | Android | 1.2.145 - Fixed | New issue |  | Closed
High | 83 |  | Dynamic Module APKs | Crashes observed after click on Live Feed - Attached log for reference | Log will attached in Email |  |  | Android | 1.2.145 - Fixed | New issue |  | Closed
High | 84 |  | Dynamic Module APKs | Random crashes observed for app launch and user in app- Attached log for reference | Log will attached in Email |  |  | Android | 1.2.145 - Fixed | New issue |  | Closed
High | 85 |  | Dynamic Module APKs | Click on VDP Widget in Dashboard . User land back to Phone Main Menu – Attached log for reference -Observed frequently in Panasonic Eluga F [Android 9] |  |  |  | Android | 1.2.145 - Fixed | New issue |  | Closed
High | 86 |  | Dynamic Module APKs | Setting Value are not persisting for Detection sensitivity, Image flip , Active time and Scene Mode- Logs Attached in Email | VDP Details Page > Change Image Flip from Normal to Rotate and Scene Mode from Night Mode to Normal> Press Bell Ring > Notifications received > Tab on Notifications > User land to VDP Details Page > Toggle On Live Feed > Observed the values |  |  | Android | 1.2.146 - Old values are coming from device status api. It is intermittent issue. Need to monitor if it is reproducible, then need to debug with server team. | New issue |  | Closed
High | 87 |  | Dynamic Module APKs | LED Indicator toggle Button getting disabled -Logs Attached in Email | VDP Setting Page > Enable LED Indicator > Press Bell Ring > Notifications received > Tab on Notifications > User land to VDP Details Page>Toggle on Live Feed> Click on Setting icon> LED Indicator in Disabled State |  |  | Android | 1.2.146 - Old values are coming from device status api. It is intermittent issue. Need to monitor if it is reproducible, then need to debug with server team. | New issue |  | Closed
High | 88 |  | Dynamic Module APKs | LED Indicator toggle Button getting Enabled - | VDP Setting Page > Disable LED Indicator > Press Bell Ring > Notifications received > Tab on Notifications > User land to VDP Details Page>Toggle on Live Feed> Click on Setting icon> LED Indicator in Enabled State |  |  | Android | 1.2.146 - Old values are coming from device status api. It is intermittent issue. Need to monitor if it is reproducible, then need to debug with server team. |  |  | Closed
High | 89 | Similar to Defect No 84 | Dynamic Module APKs | App Crash on Standby -Logs Attached in Email | User must be in VDP Details for some longer time |  |  | Android | 1.2.146 - Fixed | New issue |  | Closed
High | 90 |  | Dynamic Module APKs | Trying to change Scene Mode , App getting Crash - Logs Attached in Email | Try to change Scene Mode Setting like Normal , Night Mode , Dynamic , High light Compesation , Back light Compensation |  |  | Android | 1.2.146 - Fixed | New issue |  | Closed
High | 91 |  | Dynamic Module APKs | Scence Mode Values getting Change -Logs Attached in Email | VDP Details Page > Change Image Night Mode to Normal> Press Bell Ring > Notifications received > Tab on Notifications > User land to VDP Details Page > Toggle On Live Feed > Values again change back to Night Mode |  |  | Android | 1.2.146 - Old values are coming from device status api. It is intermittent issue. Need to monitor if it is reproducible, then need to debug with server team. | New issue |  | Closed
High | 92 |  | Dynamic Module APKs | Device Offline Text showing on VDP Details Page and it never retriev back to Online State. Though device are Online - Log Attached in email | Move device from one Room to another Room On VDP Setting Page > Press Mobile Back Button Or App Back Button > it will land you VDP details Page then device shows offline always |  |  | Android | 1.2.146/1.2.147 - Fixed | New issue |  | Closed
High | 93 |  | Universal APK | App Crash after click on Apply button in VDP Media Filter -Reproducible in Android 6 | Click on History Tab > Click on Filter By>Select Any Filter>Click on Apply Button |  |  | Android 6 | 1.2.146 /1.2.147 - Fixed (Enable MultiDex) | New issue |  | Closed
High | 94 |  | Universal APK | App Crash when trying to play sd card video | Click on History Tab > Click on SD card video to play video > Crash |  |  | Android | 1.2.146-1.2.149 - Fixed | New issue |  | Closed
High | 95 |  | Universal APK | latest videos are not updated in the top on history page. | Click on History Tab > Lastest videos are not showing on the top |  |  | Android | 1.2.146-1.2.150 - Fixed (Enable MultiDex) | New issue |  | Closed
Medium | 96 |  | Universal APK | Text need to change for Mute to Unmute and Vice Versa for Talk Button | [7 empty] | Closed
Low | 97 |  | Universal APK | Observed Full Screen icon coming in Landscape Mode | [7 empty] | Closed
Medium | 98 |  | Universal APK | Dismissing of seek bar in landscape mode when user is try to seek to different position | [7 empty] | Closed
High | 99 |  | Universal APK | Add support of VDP in feedback journey | [7 empty] | Closed
Low | 100 |  | Universal APK | Device names are showing common name for 2 different vdp device instead of showing different name as per renamed it already | [7 empty] | Closed
Low | 101 |  | Universal APK | Red button should be stable instead of blinking while recording new videos | [7 empty] | Closed
Low | 102 |  | Universal APK | Total minutes and seconds shows on Recorded videos should be common for Android & iOS, as per suggested by Abdu | [7 empty] | Closed
High | 103 |  | Universal APK | HD option not visible when first time app installed | [7 empty] | Closed

## Product Team Bug -Final
Sr No | OS | Issues/Bugs/Requirement | IIC Comments
1 | Android | Notification recd in Chinese Language on the phone , when click nothing happens , not able to remove the notification . Have to restart the phone to remove it . necessary details and snaps shared with Pratap san. | Fixed
2 | Android | Mic Icon displayed during voice activation seems to be incorrect as there is Cross line on the same - which actually represent Mic is mute . Snap shared with Pratap san | Fixed
3 | Android | When camera is accessed and Live Picture is displayed , If I scroll finger Horizontally i.e.from right to Left , Volume control is displayed and its setting changes with slide of finger . Separate Icon should be displayed for Volume control and setting change option should be displayed once Icon is pressed | Tutorial (Help Overlay added) for User Understanding
4 | Android | When camera is accessed and Live Picture is displayed , If I scroll finger Vertically i.e.from Top to Bottom , Brightness control is displayed and its setting changes with slide of finger . Separate Icon should be displayed for Brightness control and setting change option should be displayed once Icon is pressed | Tutorial (Help Overlay added) for User Understanding
5 | Android | If I use 2 fingers and stretch the Picture there seems to be Digital Zoom available . separate Icon for Zoom will be appreciated if possible | Tutorial (Help Overlay added) for User Understanding
6 | Android | When I record video and Play , The video is all in Green Colour . Video shared with Pratap san | 1. Issue in Android and not in iOS 2. Issue is not coming in video store in SD Card and Cloud 3. Issue is the with Videos recorded from app [via Record Button} 4. Solution for 3 to use Player which supports SW Encoding [Such as MX Player] 5. This can be mentioned in Device User Manual
7 | Android | Mobile used is Motorola g(6) Android ver 9
8 | Android | There is active time Icon mentioning 15s / 30S / 60S / Always options ---- Seems not working as Camera view continues beyond the time mentioned ( when call is recd and When Camera is accessed from the App ) | Active team implies, for how long the camera will remain active after live stream stops.
9 | Android | Scene mode -- options backlight / Highlight / Dynamic / Night mode ---- For backlight / Highlight / Dynamic , I could hardly make any difference in Picture Quality . Night mode seems working as it makes Picture Black and White | Please refer below link to understand more on difference https://www.burglaryalarmsystem.com/technology-news/hlc-highlight-compensation-vs-blc-backlight-compensation.html
10 | Android | Detection sensitivity -- How to use ? nothing observed once this is enabled . When camera view is stopped and access again it displays OFF every time | when detection sensitivty is set to low, it takes 7 seconds detection to trigger event, use for somebody walk around, medium will take 4s to trigger, when set to high, it triggers right now.
11 | Android | HD Image - There is option to select image Quality as HD by pressing this , once selected and camera view stopped , when Camera is accessed next time the HD selected does not remain and has to be selected again . Is there any option to select HD permanently in case client wants | Fixed
12 | Android | In Settings there is option of Cloud Video ---- What does it mean ? Do we have any Cloud storage options available ? present recording are getting stored in Phone storage only even though this option is ON | When "Cloud Video" option is ON , Videos will be store in SD Card and in Cloud . User can view both SD Card and Cloud videos in the App . Cloud videos older than 7 days will be deleted from cloud
13 | Android | LED Indicator -- Which feature is controlled using this option ? Which LED we are referring to ? What is the impact of ON and OFF ? | OFF Condition - LED Indicator would "OFF" Blue LED surrounded by Ring Button ON Condition : LED Indicator would "ON" blue LED surrounded by Ring Button
14 | Android | Crash for Click on Push Notification | Work in Progress. This issue observed in Android 8 and Android 9
15 | Android | Unlock option not available on the APP - Lock integeration | Added Feature for Unlock
16 | Ios | App Crashed Multiple times while registering Apple IOS ver 14.8.1 with Pana Bell .2. Once QR code is displayed and device is pointed towards the same , we get immediate message of “Information received” and after that display on the phone is connecting , but it failed multiple times and App also crashed 2-3 times . 7th time I was successful in registering the Device to the App . Android also it failed to connect few times . | Fixed
17 | Ios | Once Notification is recd on the IOS mobile , and we click on the notification , Camera view is still not available , we have to again press on the camera image then we can view the Live camera . On Android it pops up the camera once we click on the notification | Expected Behaviour
18 | Android | We also tested in Samsung handset Android ver 10 , We could not Play back the Video . We understand it’s a known issue and team is already working on the same | Fixed
19 | Android | There is no option to register PanaBell registered with Different ID . For Example , I have Installed one Bell at My Res with My ID and Rahul has installed another PanaBell at his residence with his ID . If I want to provide access to My panabell to Rahul , I have to provide My ID and password to him , Only access to particular PanaBell is not possible . | Not supported
20 | Android | Deleting the registered Panabell from Miraie - Delete option is available only if device is available and we are able to access the same . In case device is not available or we can no more access the device , the device can not be deleted from the App . | Fixed
21 | Android | The notification sound on the Handset / App - Most of the time user miss the notification , Request to change the same to something like Mobile Ringtone . | Currently for "Button Press", We changed notification sound and For Remaining notifications keeping same sound like other notifications of MirAIe App
22 | Android | Hardware Related - While Installing , its very diffcult to put in the small screw provided towards the bottom of the Bell - Request to consider improvement . | HW Related – Not in our scope
23 | Android | Access Denied toast is visible | Fixed

## VDP
Sr No | Main Feature | Scenario | Test Case |  | Completion Date | Android | IOS | Dependency | Steps | Android | Remarks
1 | Onboarding | Successful Journey | User must On-board VDP Succeessfully | [5 empty] | Add Device >VDP > Follow Instruction for On-boarding | Pass for both Firmware | New Firmware : Main firmware 501.0.8.32 / Wi-Fi Version 63.0.1.44
|  | Pairing failure | User must able to see On-boarding failure incase of Weak Signal , Device Low Battery , Wrong WiFi Password and SSID Name Limit |  |  | Done | Pending |  | Add Device >VDP > Follow Instruction for On-boarding | Pass
|  | Error handling | User must able to see appropriate error in case of failure 1. Device already on-boared other account 2. Device unable to pair 3. Device QR Code unable to Scan 4. Device Camera unable to Scan QR Code 5. User must able to see error for Reset Device |  |  | pending | Pending | Need to get the error flow from Rohit, in the current shared flow Onboarding error cases are not there. | Add Device >VDP > Follow Instruction for On-boarding | Pass | Crash observed for during On-boarding
2 | Dashboard widget | No last recorded video | 1. Once On-boarding done , it must show preview not available 2. Live Feed must start after enter VDP Details Page |  |  | done | pending |  | Dashboard > Widget | Pass
|  | Show last recorded snapshot | 1. Once recording started screenshot capture at Dashboard Widget |  |  | done | done |  | Dashboard > Widget | Pass
|  | Room name ,Date and Time for last recorded Snapshot | 1.. User must able to Room Name VDP Device On-boarded 2. User must able to see Date and Time for last recorded Snapshot |  |  | done | done |  | Dashboard > Widget | Pass
|  | Show connection status | 1. User must able to see Online/Offline Status of VDP device on Dashboard Widget 2. User must able to see Online in Green Dot and Offline in Gray Dot |  |  | done | done |  | Dashboard > Widget | Pass
3 | Live feed (Portrait and landscape) | Overlay Tutorial on VDP Detail page | 1. User must able to see Tutorial for Zoom , Brightness and Volume controls after on-board and click on Widget 2. Overlay Tutorial must disappear after click on "Got it" button 3. User must able to see "Slide one finger left or right to adjust volume" for Volume Controls Instruction 4. User must able to see " Pinch with two fingers to Zoom In or Out" for Zoom Video or Image 5. User must able to see " Slide one finger up or down to adjust brightness" for Video or Image Brightness control 6. User must able to see option to check overlay tutorial on Top right side ["i" icon] | [5 empty] | Dashboard >Widget > VDP Details [First time launch and icon click to show overlay again] | Pass
|  | Pinch zoom | 1. Verify Zoom In and Zoom Out for Recorded Video 2. Verify Zoom in and Zoom out for Live Feed |  |  | done | done |  | Dashboard > VDP Details Page | Pass
|  | Brightness control | 1. Verify Brightness control for Recorded Video 2. Verify Brightness control for Live feed 3. Vertical Swipe on Video Screen in details increase and decrease Brightness [up/down] for recorded video 4. Vertical Swipe on Video Screen in details increase and decrease Brightness [up/down] for Live feed |  |  | done | Done | Control UI needs to be updated | Dashboard>VDP Details Page | Pass
|  | Record live video | 1. User must able to record video and save it on local device memory 2. User must able to record video with Audio Mute 3. Verify toast message for "Recording Failed, Please try again" 4. Verify toast message for recorded video "Recorded Video Saved Successfully" 5. User must able to play recorded video in Mobile without any green colour tint and with by default player or third party player 5. User must record video in Portrait or Landspace Mode with Full Screen |  |  | done | done |  | Dashboard>VDP Details Page | Pass
|  | Mic mute/unmute | 1. Verify Enable/Disable Talk or Mute/Unmute Talk 2. Verify toast message for "Unable to initiate Talk, Please try again" |  |  | done | done |  | Dashboard>VDP Details Page | Pass
|  | Two way audio | 1. User must able to do two way communication using Mobile and VDP Microphone |  | 01-09-2021 | pending | done |  | Dashboard>VDP Details Page | Pass
|  | Change volume | 1. Verify Horizontal Swipe on Video Screen in details increase and decrease Volume [left to Right] for recorded video 2. Verify Horizontal Swipe on Video Screen in details increase and decrease Volume [Left to Right] for Live feed |  | 01-09-2021 | pending | done |  | Dashboard>VDP Details Page | Pass
|  | Change video quality HD/SD | 1.HD with white Background must capture video in SD Video Quality 2.Click on HD icon for enable or disable HD Video Quality 3.HD with Blue Background must capture video in HD Video Quality 4.User must get error notificaton "Data Consumption will be high in HD Video Quality " if user enable HD |  |  | done | Done |  | Dashboard>VDP Details Page | Pass | No have SD Card Option
|  | Capture snapshot | 1. Capture Snapshot must saved Snapshot to Album or Mobile Local Memory 2, User must able to see "Screenshot saved successfully " toast message for successfully captured snapshot 3. User must able to see error notification for Capturing failed "Capturing Failed , Please try again" |  |  | done | Done |  | Dashboard>VDP Details Page | Pass
|  | Camera Settings | 1. Disable Live Feed must disable Capture , Talk , Record , Audio , Image Flip , Active Time , Detection Sensitivity , Scene Mode 2. Enable Live Feed must enable Capture , Talk , Record , Image Flip , Active Time , Detection Sensitivity , Scene Mode | [5 empty] | Dashboard>VDP Details Page | Pass
|  | Detection sensitivity | 1. Default Detection Sensitivity should be "OFF" 2. User able to set Detection sensitity to Low , Medium , High , Off 3.User able to off "OFF" Detection Sensitity 4.User able to receive push notification if in case motion detection detected for Low , High and Medium state 5. User able to change Detection Sensitivity in Live Feed and in Recording Video | Detection sensitivity | 27-08-2021 | pending | done |  | Dashboard>VDP Details Page | Pass
|  | Image Flip | 1. Default image flip should be "Normal" 2. User can change image flip from Normal to Rotate , Mirror and Mirror & Rotate 3. User can change image flip in Live Feed and in Recording Video | Image Flip | 27-08-2021 | pending | done |  | Dashboard>VDP Details Page | Pass
|  | Scene mode | 1. Default Scene Mode should be "Normal" 2. User can change Scene Mode from Normal to Backlight, Night, Highlight and Dynamic 3. User can change scene mode in Live Feed and in Recording Video | Scene mode | 27-08-2021 | pending | done |  | Dashboard>VDP Details Page | Pass
|  | Active time | 1. Default Active time should be "15 Sec" for PIR Sensor [Pyroelectric sensor] 2. User can change Active time from 1 Sec to 15 sec .30 sec , 60 sec and Always 3. It is recommended to use 15 sec Active time for Battery Drain faster 4. User must able to see notification if he choose "Always " option [“The PIR alarm will stop working in the dormant state, and the battery will run out in the next few hours”] 5. User can change Active time in Live Feed and in Recording Video | Active time | 27-08-2021 | pending | done |  | Dashboard>VDP Details Page | Pass
4 | Display Battery Information | Show battery info in live feed | 1. User must see Battery icon in Live Feed and Recording Video [VDP Details Page>Video Recording Screen] 2. User must see "Green" icon for Battery on Charging state 3. User must see "White" icon for Battery on standby mode | [5 empty] | Dashboard >VDP Details Page | Pass
|  | Show battery info during playback | 1. User must see Battery info after playing recording video |  |  | pending | done | As per UI, we have to show battery info only on setting screen, Waiting for input from Maxwell | Dashboard >VDP Details Page | Pass
|  | Weak battery info message | 1. Low Battery Push notification must received by user |  |  | pending | done | As per UI, we have to show battery info only on setting screen, Waiting for input from Maxwell | Dashboard >VDP Details Page | Pass
5 | WiFi signal strength | Show wifi signal in live feed | 1. User must see WiFi icon in Live Feed and Recording Video 2. User must see WiFi signal strength | [5 empty] | Dashboard >VDP Details Page | Pass
|  | Show wifi signal during playback | 1. User must see WiFi Signal during playback recorded video |  |  | done | done |  | Dashboard >VDP Details Page | Pass
|  | Weak wifi signal info message | 1. User must see " Weak Wifi Signal ": "Device might experience some difficulties due to weak wifi Signal " |  |  | done | done |  | Dashboard >VDP Details Page | Pass
6 | Notification for tamper, motion detection, weak battery and bell press | Notification action to launch VDP details page | Bell Ring 1. User must able receive push notification Bell Ring >Click on push notification user must land to VDP Details Page > Press app back button or mobile device back button User move to App Home Page 2. User must able to receive notification for Bell Ring with Title "Button Pressed" and Body "Someone rang the front door bell " Motion Detection 1. User must able receive push notification Motion Detection >Click on push notification user must land to VDP Details Page > Press app back button or mobile device back button User move to App Home Page 2. User must able to receive notification for Bell Ring with Title "Motion Detection" and Body "Smart door bell detected some activity " Temper Alert 1. User must able receive push notification Motion Temper Alert >Click on push notification user must land to VDP Details Page and User able to Alert > Press app back button or mobile device back button User move to App Home Page 2. User must able to receive notification for Bell Ring with Title "Temper Alert" and Body "Your VDP device is being removed . If its not you then someone it trying to temper " Low Battery 1. User must able receive push notification Motion Low Battery >Click on push notification user must land to VDP Details Page > Press app back button or mobile device back button User move to App Home Page 2. User must able to receive notification for Bell Ring with Title "Low Battery" and Body "Your VDP Battery is low , Please charge for continue live feed " |  |  | done | done |  | Notifications | Pass
7 | Browse recorded videos | View recorded videos from SD card and cloud in a single list chronologically | 1. User must able find device recorded activity video saved in SD Card and Cloud in a Single list 2. User must able to identify device recorded activity video saved in SD Card and Saved on Cloud | [5 empty] | Dashboard > VDP Details Page>History | Pass
|  | Play recorded video in portrait and landscape | 1. User must able to device recorded activity video in Portrait and Landscape 2. User must able to control brightness and volume in Portrait and Landscape mode |  |  | pending | done | Will take up once cloud videos will be visible | Dashboard > VDP Details Page>History | Pass
|  | Filter video list by date | 1. User must able filter video saved on SD Card and Cloud by date 2. Video must show date and time for device recorded activity video |  |  | pending | done | Only done for sd card videos, pending for cloud videos. Will be completed once cloud videos will be visible. | Dashboard >VDP Details Page>History | Pass
|  | Empty video list page | 1. User must able to see Empty list if there are no recorded video available in Video List page |  |  | done | done |  | Dashboard >VDP Details Page>History | Pass
8 | Handle device connectivity status | Show device connectivity status | 1. Device status must show on widget with Green Dot for Online 2. Device status must show on widget with Gray Dot for Offline 3. Device status must show on VDP details Page title Bar with Green Dot and Online Text for Online 4. Device status must show on VDP details Page title Bar with Gray dot and Offline Text for Offline | [5 empty] | Dashboard> Widget Dashboard > VDP Details Page | Pass
|  | Enable/disable UI controls based on connectivity status | 1. User must able control options like Live Feed , Video Recording , Talk etc in Online state of device 2. User must not control options like Live Feed , Video Recording and talk etc in offline status of device |  |  | done | done |  | Dashboard > VDP Details Page | Pass
9 | SD card management | View SD card storage status | 1.App must show Available space and total available space for insert SD Card | [5 empty] | Dashboard > VDP Details Page > Setting | Pass
|  | Format SD card | 1. User must able to format SD Card via Format SD Card Journey 2. User must able to see successful message for Formatting SD Card > Click on Done iser must back to VDP Setting Page 3. Format SD Card must show available space and total space same 4. User must able to format SD card fail - "Failed to format SD Card " 5. If no SD Card insert in VDP device user must not see SD Card option in disable state |  | 03-09-2021 | Pending | Done |  | Dashboard > VDP Details Page > Setting | Pass
|  | Format error handling | 1. For SD Card Full Your SD Card is full , To make sure please delete some files from your SD Card |  |  | Done | Done |  | Dashboard > VDP Details Page > Setting | Pass
10 | Download video from SD card and cloud. | Queuing the download and downloading in background. | 1. Detail Screen > History Tab > SD card Video > Click on row item > Recorded video will play. 2, Detail Screen > History Tab > SD card Video > Click on download icon > Recorded video will download (Progress will be visible for download). 3. Detail Screen > History Tab > Cloud Video > Click on row item > Video not downloaded > Download of video. 4..Detail Screen > History Tab > Cloud Video > Click on row item > Video already downloaded > Recorded video will play. 5. User must able to download video in background 6. User can download video one by one but UI must show it would be in queue , It must be FIFO | [5 empty] | Dashboard > VDP Details Page>History | Pass
11 | Delete videos from SD card and cloud. | Ensure video meta data is also deleted. | 1. User must able to delete video from cloud and SD Card . 2. There would not be any data available for deleted video on cloud as well as SD Card | [5 empty] | Dashboard >VDP Details Page>History | Pass
12 | Offboarding and resetting camera | If offboard first, how do stop device to upload video | 1. Remove device/offboard device must remove entire data except cloud video available for particular device 2. Cloud Video must get restored afer On-board same VDP device 3. Cloud Video must not restored if it is stored more than 7 days on cloud | [5 empty] | Dashboard > VDP Details Page > Setting | Pass
|  | If reset first, force device to offboard or onboard. | 1. User must able offboard or onboard n times by reseting device 2. Performance of device should not effect after offboard or onboard again |  |  | pending | pending | For now, just show the message before off boarding. Ask for the UI | Dashboard > VDP Details Page > Setting | Pass
|  | Device off state | If Device offline for longer time then user must able to get message on VDP details Page " Please check the device is online if problem persists try to onboard again" | [5 empty] | Device Power State Off | Pass
16 | Localization |  | Application must support localization for Hindi , Marathi , Tamil , Telugu , Bengali and Thai |  | 25-09-2021 | pending | pending | All existing vdp strings are translated, need to integrate into the app. | Dashboard>Setting >Change language | Pass
17 | VDP disable for Sri Lanka User |  | User should not see VDP in Add Device | [5 empty] | Login as Sri Lanka User | Pass
18 | Setting Page | Cloud video enable/disable | 1.User must able to Enable/Disable Cloud Video 2.It make sure Video should not save in case it is disable state 3.It make video must save in case it is enable state 4. Cloud video must delete automatically from cloud server after seven days | Cloud video enable/disable |  | pending | done | Will take up once cloud videos will be visible | VDP Details Page>Setting>Cloud | Pass
|  | LED Indicator | 1.User must able to Enable/Disable LED Indicator 2.Make sure LED Indicator should OFF in case it is disable 3.Make sureLED Indicator should ON in case it is enable | LED Indicator | 27-08-2021 | pending | done |  | VDP Details Page >Setting >LED Indicator | Pass
|  | Edit VDP device name | 1. User can edit Device name with maximum 20 character including space 2. Click on "Update Name">user must able to see " Device is renamed successfully" | [5 empty] | Dashboard > VDP Details Page > Setting | Pass
|  | Show VDP product information and firmware details | 1. User must see VDP product details like Model No , Firmware Version , WiFi Version and Device ID | [5 empty] | Dashboard > VDP Details Page > Setting | Pass
|  | Move device between different rooms | 1. User must move VDP device from one room to another [Setting >Room Assigned] 2. After move App must show " Device is moved sucessfully" 3. User must able to see VDP device in moved Room | [5 empty] | Dashboard > VDP Details Page > Setting | Pass
19 | Unlock Door | Unlock Door from VDP Details Page | 1. Unlock Door option must need to available on VDP details Page 2. Click on Unlock button user must see "Unlock Door" screen for input Password 3. After input Password and click on Unlock button .. Door must need to unlock/open 4. Click on Cancel Button , User must back to VDP details Page 5. For successful password , User get notification "You door is unlocked" 6. For Wrong Password , User get error notification " Enter a valid password" 7. No Response from VDP, User get error notification " Your request could not complete , Please try after some time ." 8. By default password , please check the user manual | [5 empty] | Dashboard > VDP Details Page | Pass
|  | Reset door lock password | 1. Reset door lock password option to be available on VDP setting page. 2. Click on "Reset door lock password" must open "Reset Password" Page 3. Need to input Old Password , new Password and Confirm Password for Reset Password 4. For New Password , User must enter characters between 8-20 between and mix with letters and numbers 5. New Password and Confirm Password must need to match . If not match user must able to see " Password doesn't match" 6. If user enter character below 8 and not mix with letters and numbers then he must able to see error message in red colour 7. If user not enter correct old password then he must able to see "Password doesn't match" 8. User must able to see " Your password has reset successfully" after successful reset 9. User must able to back Setting Page after reset password successfully | [5 empty] | Dashboard > VDP Details Page > Setting | Pass

## Product Team Bug (hidden)
Sr No | OS | Issues/Bugs/Requirement | IIC Comments | Remarks | Dev Comments | IIC Comments
1 | Android | Notification recd in Chinese Language on the phone , when click nothing happens , not able to remove the notification . Have to restart the phone to remove it . necessary details and snaps shared with Pratap san. | Prateek working on it | Fixed | Fixed | Fixed
2 | Android | Mic Icon displayed during voice activation seems to be incorrect as there is Cross line on the same - which actually represent Mic is mute . Snap shared with Pratap san | Need to make change in below text for Mute and Unmute | Abdu will discuss with Rohit and provide new UI. | Fixed | Fixed
3 | Android | When camera is accessed and Live Picture is displayed , If I scroll finger Horizontally i.e.from right to Left , Volume control is displayed and its setting changes with slide of finger . Separate Icon should be displayed for Volume control and setting change option should be displayed once Icon is pressed | Separate button required for brightness and volume control as per Product Team |  | Fixed | Tutorial (Help Overlay added) for User Understanding
4 | Android | When camera is accessed and Live Picture is displayed , If I scroll finger Vertically i.e.from Top to Bottom , Brightness control is displayed and its setting changes with slide of finger . Separate Icon should be displayed for Brightness control and setting change option should be displayed once Icon is pressed | Separate button required for brightness and volume control as per Product Team |  | Fixed | Tutorial (Help Overlay added) for User Understanding
5 | Android | If I use 2 fingers and stretch the Picture there seems to be Digital Zoom available . separate Icon for Zoom will be appreciated if possible | Zoom in and Zoom Out Option required to change Zoom as per Product Team |  | Fixed | Tutorial (Help Overlay added) for User Understanding
6 | Android | When I record video and Play , The video is all in Green Colour . Video shared with Pratap san | Unable to reproduce . Will keep testing |  | Video is working fine in Laptop, showing greeen overlap in 3rd party player app. Not in our control. Reported to Maxwell waiting for his response. | 1. Issue in Android and not in iOS 2. Issue is not coming in video store in SD Card and Cloud 3. Issue is the with Videos recorded from app [via Record Button} 4. Solution for 3 to use Player which supports SW Encoding [Such as MX Player] 5. This can be mentioned in Device User Manual
7 | Android | Mobile used is Motorola g(6) Android ver 9 | OK
8 | Android | There is active time Icon mentioning 15s / 30S / 60S / Always options ---- Seems not working as Camera view continues beyond the time mentioned ( when call is recd and When Camera is accessed from the App ) | Required more details | Need to test with Ubell App and See Performance | Behaviour of Ubell and Miraie app is same. Neeraj will discuss with PM Team | Active team implies, for how long the camera will remain active after live stream stops.
9 | Android | Scene mode -- options backlight / Highlight / Dynamic / Night mode ---- For backlight / Highlight / Dynamic , I could hardly make any difference in Picture Quality . Night mode seems working as it makes Picture Black and White | Required more details | Need to test with Ubell App and See Performance | Behaviour of Ubell and Miraie app is same. Neeraj will discuss with PM Team | Please refer below link to understand more on difference https://www.burglaryalarmsystem.com/technology-news/hlc-highlight-compensation-vs-blc-backlight-compensation.html
10 | Android | Detection sensitivity -- How to use ? nothing observed once this is enabled . When camera view is stopped and access again it displays OFF every time | No notification received for user to know detection | Need to test with Ubell App and See Performance | Behaviour of Ubell and Miraie app is same. Neeraj will discuss with PM Team | when detection sensitivty is set to low, it takes 7 seconds detection to trigger event, use for somebody walk around, medium will take 4s to trigger, when set to high, it triggers right now.
11 | Android | HD Image - There is option to select image Quality as HD by pressing this , once selected and camera view stopped , when Camera is accessed next time the HD selected does not remain and has to be selected again . Is there any option to select HD permanently in case client wants | Need option for HD enable always in Setting Page as per Product Team |  | This feature will be provided once device status api support is added. | Fixed
12 | Android | In Settings there is option of Cloud Video ---- What does it mean ? Do we have any Cloud storage options available ? present recording are getting stored in Phone storage only even though this option is ON | Team are working |  | Not aware of this feature. | When "Cloud Video" option is ON , Videos will be store in SD Card and in Cloud . User can view both SD Card and Cloud videos in the App . Cloud videos older than 7 days will be deleted from cloud
13 | Android | LED Indicator -- Which feature is controlled using this option ? Which LED we are referring to ? What is the impact of ON and OFF ? | Ok | Explain Virender san for its working |  | OFF Condition - LED Indicator would "OFF" Blue LED surrounded by Ring Button ON Condition : LED Indicator would "ON" blue LED surrounded by Ring Button
14 | Android | Crash for Click on Push Notification | Need to reproduce issue |  | Reproduce in Android 9, as per logs it is Tombstone crash. Reported to Maxwell, waiting for his response. | Work in Progress. This issue observed in Android 8 and Android 9
15 | Android | Unlock option not available on the APP - Lock integeration |  |  | Queried Maxwell. Waiting for his response. | Added Feature for Unlock
16 | Ios | App Crashed Multiple times while registering Apple IOS ver 14.8.1 with Pana Bell .2. Once QR code is displayed and device is pointed towards the same , we get immediate message of “Information received” and after that display on the phone is connecting , but it failed multiple times and App also crashed 2-3 times . 7th time I was successful in registering the Device to the App . Android also it failed to connect few times . |  |  |  | Fixed
17 | Ios | Once Notification is recd on the IOS mobile , and we click on the notification , Camera view is still not available , we have to again press on the camera image then we can view the Live camera . On Android it pops up the camera once we click on the notification |  |  |  | Expected Behaviour
18 | Android | We also tested in Samsung handset Android ver 10 , We could not Play back the Video . We understand it’s a known issue and team is already working on the same |  |  | Fixed | Fixed
19 | Android | There is no option to register PanaBell registered with Different ID . For Example , I have Installed one Bell at My Res with My ID and Rahul has installed another PanaBell at his residence with his ID . If I want to provide access to My panabell to Rahul , I have to provide My ID and password to him , Only access to particular PanaBell is not possible . |  |  | Not supported | Not supported
20 | Android | Deleting the registered Panabell from Miraie - Delete option is available only if device is available and we are able to access the same . In case device is not available or we can no more access the device , the device can not be deleted from the App . |  |  | Fixed | Fixed
21 | Android | The notification sound on the Handset / App - Most of the time user miss the notification , Request to change the same to something like Mobile Ringtone . |  |  | That is feasible. Currently for "Button Press", we are changing the sound of notification. Do we have to change the sound for other notifications? | Currently for "Button Press", We changed notification sound and For Remaining notifications keeping same sound like other notifications of MirAIe App
22 | Android | Hardware Related - While Installing , its very diffcult to put in the small screw provided towards the bottom of the Bell - Request to consider improvement . |  |  | HW Related – Not our response | HW Related – Not in our scope
23 | Android | Access Denied toast is visible |  |  | Fixed. Showing dialog as per UI team message. | Fixed

## Dynamic module bugs (hidden)
Bug Num | Issue Description | Dev Status | Test Comments
1 | Live feed full screen is not working getting white screen and need to kill the app to use VDP again. (App crashes) | Fixed | Pass
2 | Live Video Record option is not working getting white screen and need to kill the app to use VDP again. (App crashes) | Fixed | Pass
3 | Full screen option are showing without play any videos from history tab and if user tap on full screen option getting white screen and need to kill the app to use VDP again. (App crashes) | Fixed | Pass
4 | SD card videos are not working when tap on full screen option getting white screen and need to kill the app to use VDP again. (App crashes) | Fixed | Pass
5 | Audio toggle button is enabling when user tap on unmute button. | Not an issue, since behaviour is same in Ubell app | Pass
6 | When active time change to always user not getting pop up message showing that (The PIR alarm will stop working in the dormant state, and the battery will run out in the next few hours) | Fixed | Pass
7 | Cloud videos are not playing from history tab until unless video downloaded (No response). | In Android, cloud videos can't be directly played, it has to be downloaded first before playing. | Pass
8 | Present used data details are not showing for T card (SD card) | Fixed | Pass
9 | App crash after launch VDP devices | Fixed | Pass
10 | App crash after click on Setting icon | Fixed | Pass
11 | For Cloud Video Download , User unable to download after press on Cloud Thumbnail. | Fixed | Pass
12 | Audio checkbox should be enabled, when opening vdp detail screen | Fixed | Pass
13 | Less cloud videos are showing in history tab for selected date | Fixed
14 | in Dark Mode Font Colour change to Blue for some thumbnails and text - Android 11
15 | App Crash after click on "Yes" Button in VDP On-boarding Journey - Android 8.1.0 [Vivo]
16 | Font Icons are in Boxes for Entire VDP - Android 8.1.0
17 | HD Option not persistant and not visible
18 | App Crash after click on Notification and User should land Dashboard - Android 9
19 | Video Door Phone visible in Add Device [Dashboard] and in Room Management for Sri Lanka , Singapore and Thailand User